## Slide 1: Independent Project Review
Keeping Projects on Track

## Slide 2: Proposing a Methodology … for Independent Project Review (IPR)
Independent – to a certain extent!
Review - with ‘grassroots’ input.
Practical, Focused Action Plans
Lifecycle Tracking of Project Concerns
Emphasis on Continuous Assessment.
Review ‘report’ is NOT the main focus.

## Slide 3: Reference Projects
Optara Refinery Upgrade (2015)
    Belgium – Total
USAN Subsea Manifold (2008)
    Nigeria - Cameron / Total
OKLNG (2007)
    Nigeria – BG/Chevron/Shell/NNPC
Bonga Subsea Field Dev. (2005)
    Nigeria – Shell
LUL Connect Project (2004)
    London Underground Ltd
West Libyan Gas Pipeline (2003)
    Libyan Desert – Agip Gas

## Slide 4: Reference Projects – ‘eventual finish’
Five projects
Each finished ‘eventually’
… but we ask, for your project …
Is ‘eventually’ good enough?
Optara Refinery Upgrade (2015)
    Belgium – Total
USAN Subsea Manifold (2008)
    Nigeria - Cameron / Total
OKLNG (2007)
    Nigeria – BG/Chevron/Shell/NNPC
Bonga Subsea Field Dev. (2005)
    Nigeria – Shell
LUL Connect Project (2004)
    London Underground Ltd
West Libyan Gas Pipeline (2003)
    Libyan Desert – Agip Gas

## Slide 5: Reference Projects – ‘success secret’
None of these had regular formal ‘Project Reviews’.
But what they did have …
Was great ‘tracking’ and ‘communications’.
Optara Refinery Upgrade (2015)
    Belgium – Total
USAN Subsea Manifold (2008)
    Nigeria - Cameron / Total
OKLNG (2007)
    Nigeria – BG/Chevron/Shell/NNPC
Bonga Subsea Field Dev. (2005)
    Nigeria – Shell
LUL Connect Project (2004)
    London Underground Ltd
West Libyan Gas Pipeline (2003)
    Libyan Desert – Agip Gas

## Slide 6: Reference Projects - Feedback
Bonga Subsea Field Dev. (2005)
    Nigeria – Shell
    “This was the first time I had seen this approach for management of project issues. My project had a list of more than 450 issues when it was handed to me, well over 50 of them mission critical. David’s system provided a means of tracking and accountability, making it possible to resolve all of the major issues in a structured way during a 4 month intensive period leading up to successful achievement of first oil.“
          David Webster, Project Manager for First Oil, Shell Bonga Subsea Field Development.
Project Review - involves understanding the Issues

## Slide 7: Reference Projects - Feedback
LUL Connect Project (2004)
    UK – LUL
    “There are over 600 locations required as part of the Telecommunications Network Integration Project. The techniques used on the power upgrade portion of this project to compare and contrast conflicting information sources were very impressive. I found this kind of analysis invaluable in keeping all of the sources correct in the face of continually evolving objectives.“
          Andrew Smart, Project Commissioning Manager, London Underground Ltd.
Project Review - deals with conflicting data sources.

## Slide 8: Reference Projects - Feedback
Optara Refinery Upgrade (2016)
    Antwerp, Belgium – Total
    “Never before have we seen such clarity on Project Concerns. The communications process running in the background, ensured the continual availability of quality information not just for the Risk Management team but also for the Planners.“
          Andrew Donlan, Planning Manager, Total
Project Review - needs ‘clarity on Project Concerns’

## Slide 9: Some Myths Busted
There are some commonly held beliefs about the Independent Project Review that have their basis in history.
      An Austere and Serious Review Team(myth)
      Everything Stops for the IPR(myth)
      Spare the Rod and Spoil the Project(myth)
But have no place in a correctly conducted review.

## Slide 10: Myth 1 – Superiority Gradient
An Austere and Serious Review Team(myth)
    The project is doing it’s best given the circumstances of it’s execution. (truth)
    The main objective of the review is to compare the project’s health now with how it could have been. (truth)
    Projects are made of people, the review team included. It’s not a case of ‘superior’ instructing ‘inferior’. (truth)

## Slide 11: Myth 2 – The Intrusive Review
Everything Stops for the IPR(myth)
    The review is a non-intrusive look into the project’s operation. (truth) The interviews and site visit needed in the review should be built into the normal operation of the project. (truth)
    No ‘preparation’ is needed by the project team. (truth)
    An IPR is NOT an ‘audit’. (truth)

## Slide 12: Myth 3 – Punitive Judgement
Spare the Rod and Spoil the Project(myth)
    The review is an opportunity for improvement. (truth)
    There is no ‘I told you so’ in an IPR. (truth)
    Everything is forward looking. (truth)
    No post mortem, no blame, no punishment. Instead, just assessment of the current status and collective analysis of the gap and how to close it. (truth)

## Slide 13: How it’s done – The PHC way.
The Review process in four phases:
    Gathering of Documents
    Site Visit and Interviews
    Management Workshops
    The Final Report

## Slide 14: How it’s done – Document Pre-read
Project documents are requested for content analysis and to highlight the need for any missing documents that should be in use at the current phase.
Traditional | The PHC way
One-off study dedicated to the review. | We build project outline ‘lists’ that are useful to the project as well as the review. [The SCALPED lists – Schedule, Concerns, Actions, Locations, People, Events, Deliverables]
This review is happening – get used to it! | We get buy in from the entire compliment of project staff by publishing a site dedicated to the Review and gathering contributions from ‘grass roots’ level.
Strict timetable, intrusive, | Relaxed, flexible timetable, not ‘extra work’ for the Project Team, fits in with normal Project activity.
Gap analysis on key documents | Documents and procedures are collected in one of the project outline lists as continual review throughout the project.

## Slide 15: How it’s done – Site Visit and Interviews
The site visit and interviews are important information sources for the review. Interactions trigger questions about what’s ‘going on’ in the project, helping the IPR team to form a consolidated overall impression of project status.
Traditional | The PHC way
Site visit for observation. | To us, the site visit is just another opportunity to gather information for the database.
Interviews for information gathering. | The interviews also are simple input mechanisms for the reviewers to gather project status.
Analysis of interactions for report brief. | For the review, the most important feature in the database is the Concerns list, the main element for reporting on review findings and improvement strategies.
Gap analysis on key documents | Secondary information in the database is held in the other lists that support understanding of the project’s Concerns.
Time at site is kept to a minimum. | We tend to stay on site longer and schedule key meetings as a ‘tick list’ on a flexible timetable. Data gathering, analysis and reporting is a continuous interleaved exercise.

## Slide 16: How it’s done – Management Workshops
A preliminary briefing of management on the report findings is done from the report draft. Discussions are incorporated into the draft and the final report is issued. The report findings are per section, each with an action strategy for ongoing improvement.
Traditional | The PHC way
Workshops are formal, intrusive, inefficient. | Workshops are information gathering sessions. No numbers, no evaluation, just rapid feed ‘input’.
Interactions don’t catch all. | All interactions are recorded and analysed after the meeting. Consolidated information is SCALPED for absorption into the IPR database.

## Slide 17: How it’s done – The Final Report
The findings are collated into a final report that presents an action plan with a list of action items for tracking to completion.
Traditional | The PHC way
The report comes at the end. | The management will be able to monitor the progress of the report throughout the review.
The report is a work of art! | The final report will be compiled from the database and will consist mainly of single sheet Concern Summaries.
The report is a one-off. | The report is a living document. If used within the context of the IPR database, it is continually adjusted and the progress of action strategy implementation can be seen in dashboard form right up to completion.

## Slide 18: Key Focus Areas
There are Seven:
    Coordination
    Team Building
    Monitoring and Control
    Change Management
    People Planning
    Organisation Management
    Documents and Information

## Slide 19: Key Focus Areas (1 of 7)
Coordination
    When materials or information in the project moves from one place to another, either regularly or in single one-time movements, there needs to be special attention given to the process.
    It should be in a coordination process that identifies and stipulates a hierarchy of coordination procedures.
    A coordination procedure integrates the objectives of the various project functions (planning, operations, materials management etc.)

## Slide 20: Key Focus Areas (2 of 7)
Team Building
    For a project specific team, team building programme can be an asset in pursuit of an organizational ‘vision’.
    The team members must see where they fit in.
    The whole team’s actions and efforts contribute towards the project’s vision.

## Slide 21: Key Focus Areas (3 of 7)
Monitoring and Control
    Progress of the current workforce needs continuous reassessment.
    We track the required quality of the planned deliverables.
    We track availability of resources needed to manage the project requirements and priorities.

## Slide 22: Key Focus Areas (4 of 7)
Change Management
    There must be in the project a system that can control changes and ultimately assist in controlling cost and schedule.

## Slide 23: Key Focus Areas (5 of 7)
People Planning
    Organizational development and human resource planning with special emphasis on team members who may be destined for later project organizational assignments.

## Slide 24: Key Focus Areas (6 of 7)
Organisational Management
    Existing organizational management systems and procedures that have been reviewed, validated, and updated as necessary for compatibility with the project and its planned objectives.

## Slide 25: Key Focus Areas (7 of 7)
Documents and Information
    We know that document management practices have grown beyond the traditional ‘file room’ concept.
    Information technology methods and computer tools have been created and tested in practice so as to provide the reliable and efficient handling of texts and data.
    It is essential to project health that document control must be effective and transparent.

## Slide 26: The Golden Rules.
Achievement & Bad Performance – recognise both.
Listen and Learn - then talk.
Leverage complainers and detractors.
Build a team - don’t destroy it.
Find Consensus – a prelude to success.
Never say ‘I told you so’

## Slide 27: Rule 1 – Recognise Achievement
Achievement & Bad Performance – recognise both.
  Project Reviews tend to focus on the negative.
  But there is value in leveraging achievement, as well as in correction and improvement.
  Project Participants are human – recognition of achievement is a key motivation factor.

## Slide 28: Rule 2 – Listen and Learn, then Talk
Pre-conceived Ideas Not Allowed.
  The key to an improvement strategy is in the dialogue with project participants.
  A ‘preaching’ reviewer builds barriers to communication!
  The project participants know what’s wrong – hear them.
  Humility, openness and professionalism – enables desired frankness from the Project Team.

## Slide 29: Rule 3 – Hear Gripes and Complaints
Complainers and Detractors – Leverage Them.
  The IPR is perfect for venting frustrations – let it flow!
  Truth will emerge. Analysis differentiates fact from fiction.
  The greatest benefit is in first flush of dialogue – make strategic cut-offs for contributors.
  Keep bringing the meeting back to the discussion theme.

## Slide 30: Rule 4 – Build the Team
Build the Team – Don’t Destroy It.
  The IPR can be used to foster team spirit – leverage this!
  Use the IPR to clarify interfaces between project participant sections.
  Concerns related to Internal Politics are simplest to recognise, and with proper clarification, easy to resolve.
  Team politics may be the biggest Concern – high value resolution of this order pays for an IPR over and over.

## Slide 31: Rule 5 – Find Consensus
Find Consensus – A Prelude to Success.
  The best way to implement improvement is at the grassroots level.
  Any ideas brought in by the IPR team will be made to appear from the result of joint efforts.
  Wider acceptance of review finings is related to wider involvement of ALL project participants, at all levels in the hierarchy.

## Slide 32: Rule 6 – Never say, “I told you so”
Never say I told you so.
  Especially on successive reviews were previous action strategies were not carried out, we avoid the temptation to beat this drum!
      Circumstances sometimes don’t allow implementation.
      Sometimes the implementation has had lower priority.
  Each IPR is a new chapter for seeking new opportunities for improvement, not for criticising past lapses.

## Slide 33: Timeline Walk Through.

## Slide 34: For Your Project – What next?
For IPR-Related project news – visit [web address for the Company portal].
Workshops plans have simplicity at their core.
Individual Interviews are direct, focussed and respectful of the individual’s time.
Easy access to the project portal for ad hoc contributions in the context of the individual’s work.
Enquiries:
david.winter@order-efficiency.com
“If you can visualise a simple system like this for an Independent Project Review applied to one of your projects, then please let us know.“ David Winter